## Slide 1: Agile Foundations with Scrum
Session 7: Sprint Reviews and Retrospectives

## Slide 2: Scrum Team Ceremonies
Sprint Planning
Daily Scrum
Backlog Grooming
Sprint Demo/Review
Sprint Retrospective/Lessons Learned
It is important to remember that these meetings are a cycle.

## Slide 3: Definition of Done
Definition of Done:
The story meets the criteria established by the team to consider work to be completed (e.g. the code has been successfully tested in a specific environment).
The product owner has accepted the story as done based on the acceptance criteria.
Notes: The product owner can guess that a story is right sized, but only the team can accept a story into sprint planning.
The confirmation of size is a guess.
Sometimes the confirmation of size requires a research task, those tasks should be scheduled into the sprint work of the team (if the team is doing the research). Otherwise the responsibility for the research should follow a common sense model. The team members who can make the most sense out of the resulting information should be accountable for the research.

## Slide 4: Retrospective and Review Overview
Purpose: To enable the inspect and adapt process for the team.
Attendees: Entire Scrum Team (PO, SM, Dev Team), stakeholders can sit in.
Process:
  Work completed is summarized and/or demonstrated.
  Work committed to and not completed is summarized.
  Team feedback is gathered and prioritized for analysis.
  Top priority team feedback in analyzed.
  An action plan is identified.
  Previous action plan is reviewed and results discussed.

## Slide 5: Goals of Retrospective and Review
Empower the entire team to continuously improve.
  The action plan should be S.M.A.R.T (specific, measurable, attainable, relevant, and time-based).
Enable the inspection and adaption cycle for the team.
Create a climate of safety, transparency, and honesty.
Provide information on best practices to the organization.
  The new practices developed by a team seeking to solve a problem could likely prevent similar problems on other teams.

## Slide 6: Retrospective and Review Prerequisites
Before Sprint Planning the team should have:
“closed” the sprint – the status of all work has been properly updated.
Completed and incomplete work are identified.
The facilitator has a method for collecting feedback that the team is aware of in advance.
The facilitator has more than one method for root cause analysis prepared and is confident they know how to apply each method effectively.

## Slide 7: Root Cause Analysis
“A root cause is the absence of a best practice and the failure to apply knowledge that would have prevented the problem.”
Root cause analysis is the process of identifying that knowledge and/or best practice.
Once identified, actions should be identified to ensure that the knowledge or best practice properly employed in the future.

## Slide 8: Root Cause Analysis Techniques
Five whys
FMEA (Failure Mode and Effects Analysis):
FTA (Fault Tree Analysis)
CRT (Current Reality Tree)
Ishikawa (Cause-and-Effect) Diagrams
Kepner-Tregoe
RPR (Rapid Problem Resolution)

## Slide 9: Action Plan
Action plan is the natural result of a root cause analysis.
The action plan describes actions or process changes that will be made to change an unwanted outcome.
Actions should adhere to the S.M.A.R.T. standard
  Specific
  Measurable
  Achievable
  Relevant
  Time-based.

## Slide 10: Our Class Retrospective
Review
  What information was covered?
  What outcomes were achieved?
  What wasn’t done?
Retrospective
  Gather feedback
  Prioritize feedback
  Root cause analysis
  Create Action plan

## Slide 11: Review: What Information Was Covered
Scrum Basics: The Agile Manifesto and “How Scrum Works”
Scrum Roles (Scrum Master, Product Owner, and The Team)
  Scrum Master is the process expert, not a project manager.
  Product Owner one person with decision making power, but cannot override the Team’s estimates.
  Product owner controls scope, release timing, business priorities, training, and stakeholder relationships.
  The Team is a multi-disciplinary team that builds, tests, and ships.
  Waterfall roles and Scrum roles aren’t the same.

## Slide 12: Review: What Information Was Covered (cont.)
Scrum Ceremonies
  Scrum ceremonies cycle: Backlog Grooming, Sprint Planning, Daily Scrum (standup), Sprint Review, and Sprint Retrospective.
  Collaborative estimation of User stories by consensus using story points.
  Story decomposition and task identification.
  Product vs. Sprint backlogs: ownership, protected from changes (or not) and authority.
  Time-boxing.
  The definition of done.
  Inspect and adapt cycle.

## Slide 13: Review: Outcomes
Training Goal: Can you participate in a Scrum Team? (note the lack of adjectives and adverbs)

## Slide 14: Review: What didn’t get done
We haven’t gottn to Scrum Values and Culture.

## Slide 15: IT’S STICKIES TIME
We are doing a variation the keep doing, stop doing, try doing… retro game.

## Slide 16: Prioritization of Feedback
Is there a show stopper/did we have a cataclysmic event?
  Yes! Let’s do a root cause analysis on that issue (FTA/Ishikawa/RPR).
  No! Let’s do a Pareto Analysis on the feedback to identify the 20% of work that should address 80% of our issues.

## Slide 17: Analysis of Top Priority Feedback
Themes
  Curriculum Design
  Facilitation
  Prior Knowledge Overestimation
  Pacing
  Assessment Design
  Logistics

## Slide 18: Analysis of Top Priority Feedback
Pareto Chart

## Slide 19: What should we address?
Focus on what actions will have the greatest impact.

## Slide 20: Taking Action
Make actions S.M.A.R.T.
Track progress.
Follow up, measure, confirm.
Make it transparent (the whole team/enterprise can see it if they want to)
The entire team is responsible and accountable (but individuals can step forward to take responsibility for deliverables).

## Slide 21: Learn More
SharePoint: http://ilink/its/agile/
  All the materials from the class.
  Free books and articles on Agile, Scrum, and Kanban.
  Templates and Tools.
  Research projects and findings (coming soon).
  Agile dictionary (coming soon).