## Task Analysis
Target Task | Supporting Task/Skill | Supporting Task/Skill | Supporting Task/Skill | Supporting Task/Skill | Supporting Task/Skill | Supporting Task/Skill
Facilitate a sprint retrospective | Schedule the retrospective at the appropriate time | Schedule the retrospective at the end of the sprint.
| Facilitate an agenda to cover necessary activities | Summarize work completed | Use a Sprint backlog burndown
| Facilitate an agenda to cover necessary activities | Identify work not completed | Use a Sprint backlog burndown
| Facilitate an agenda to cover necessary activities | Solicit team feedback | four quadrant chart (Well, Not Well, Ideas, Shout Outs)
| Facilitate an agenda to cover necessary activities | Solicit team feedback | Survey monkey surveys
| Facilitate an agenda to cover necessary activities | Analyze team feedback | Prioritization of issues | Consensus decision making
| Facilitate an agenda to cover necessary activities | Analyze team feedback | Prioritization of issues | Pareto Analysis: Data driven prioritization
| Facilitate an agenda to cover necessary activities | Analyze team feedback | Root cause analysis | How to conduct a root cause analysis | Five whys: Prone to confirmation bias.
| Facilitate an agenda to cover necessary activities | Analyze team feedback | Root cause analysis | How to conduct a root cause analysis | FMEA (Failure Mode and Effects Analysis):
| Facilitate an agenda to cover necessary activities | Analyze team feedback | Root cause analysis | How to conduct a root cause analysis | FTA (Fault Tree Analysis): Good for identifying combinations of factors when the root cause is not obvious.
| Facilitate an agenda to cover necessary activities | Analyze team feedback | Root cause analysis | How to conduct a root cause analysis | CRT (Current Reality Tree): Good for process problems and human error identification.
| Facilitate an agenda to cover necessary activities | Analyze team feedback | Root cause analysis | How to conduct a root cause analysis | Ishikawa (Cause-and-Effect) Diagrams: Allows for multiple perspectives, but does not prioritize solutions.
| Facilitate an agenda to cover necessary activities | Analyze team feedback | Root cause analysis | How to conduct a root cause analysis | Kepner-Tregoe: process designed to eliminate confirmation bias
| Facilitate an agenda to cover necessary activities | Analyze team feedback | Root cause analysis | How to conduct a root cause analysis | RPR (Rapid Problem Resolution): Good for when the root cause is very unclear.
| Facilitate an agenda to cover necessary activities | Analyze team feedback | Root cause analysis | How to measure the quality of your analysis. | Identify confirmation bias.
| Facilitate an agenda to cover necessary activities | Action plan | Scientific method
|  | Action plan | Pareto Analysis: Data driven prioritization