## Session 5 Task Analysis
Target Task | Supporting Task/Skill | Supporting Task/Skill | Supporting Task/Skill
Set up a burndown chart | identify the data points measured by a burndown chart
Set up a burndown chart | Have a copy of the Burndown template.
Set up a burndown chart | Have a committed sprint blacklog | Stories have been estimated using story points
Facilitate planning poker | Understand the fibbonacci sequence.
Facilitate planning poker | Have a fibbonacci deck. | Present the user story and facilitate Q&A with the product owner.
Facilitate planning poker | Have an established baseline story for the team.
Estimate a story using story points | Compare the story to the baseline story. | Establish a baseline story for the team to compare other stories against.
List the goals of sprint planning | Know what a sprint backlog is.
List the goals of sprint planning | Know what an effective sprint goal is.
Document Tasks required to complete a user story. | Identify tasks required to satisfy a user story | Establish the definition of done for the team. | Capture the tasks and associate them with the story. | Identify the accountable party for each task.

## 7 deconstruction methods
Perspective | Method
How the user story is executed | Workflow Steps
How the user story is executed | Business Rules
How the user story is executed | Test Cases
What is done during the user story. | CRUD/Operations
What is done during the user story. | Input Options/Platform
What is done during the user story. | DataTypes/Parameters
Who executes the user story | Roles

## Goals of Sprint Planning
Have a sprint goal
Have a sprint backlog
Know exactly what needs to get done for the sprint to be completed
Know who is going to get the work done for the sprint to be completed
Have an execution plan to manage external dependencies and internal dependencies.