## Scrum Team RACI
Role: | [Scrum Master] | [Product Owner] | [Dev Team]
Team Member Name(s)
Product Backlog Management
Adding to backlog | I | A/R | C
Prioritizing in backlog | I | A/R | C
Removing from backlog | I | A/R | C
Nominating sprint goals | I | A/R | C
Resolving prioritization disputes | I | A/R | C
Stakeholder Communications | I | A/R | C
Sprint Backlog Management
Adding to backlog | C/I | C | A/R
Prioritizing the backlog | C/I | C | A/R
Removing from backlog | C/I | C | A/R
Setting sprint goals | C/I | C | A/R
Resolving prioritization disputes | C/I | C | A/R
Scrum Facilitation
Facilitate daily standup | A/R | I | I
Facilitate weekly requirement review/ Backlog Grooming | A/R | I | I
Facilitate Bi-Weekly Planning | A/R | I | I
Monitor bi-weekly progress metrics | A/R | I | I
Monitor project progress metrics | C/I | A/R | C
Monitor release progress metrics | C/I | A/R | C
Communicate release windows | C/I | A/R | C
Facilitate the removal of obstacles to delivery for the Development team | A/R | I | C
Release Planning
Identify MVP from backlog | I | A/R | C/I
Adding planned work to a release backlog | C/I | A/R | C/I
Create Sprint Roadmap | C/I | A/R | C/I
Create dependency management plan | C/I | A/R | C/I
Testing and Quality Assurance
Write test plans | I | C/I | A/R
Publish testing results | I | C/I | A/R
Write test scripts | I | C/I | A/R
R = Responsible, A = Accountable, C = Consulted, I = Informed

## Scrum Team Roles
Role |  | Individual(s) | Location
Scrum Master |  | Emily Hall | MO-10
Product Manager |  | Kevin Gray | MO-9
Dev. Team | Engineer(s) | Prashanth Garani | Museum Wing-2
|  | Susmitha Thokala | Museum Wing-2
|  | Steve Ouellette | Museum Wing-2
|  | Loretta Budd | Museum Wing-1
| Product Analyst | Faye Katen | MO-12
| Release Analyst | Rose Anzalone | MO-12
| Quality Analyst(s) | Michael Murphy | MO-9
|  | Pat DelGiudice | MO-12